## Tabelle1
Salamantex Assignment
Task name | Task description | Estimated time (hrs) | Actual time (hrs) | From | To
Research |  | 1:00 | 1:00 | 20:30 | 21:30
Overthinking & Planning (Paper) |  | 2:00 | 1:30 | 21:30 | 23:00
Creating model |  | 1:00 | 0:30 | 8:00 | 8:30
Start backend project /setup |  | 0:10 | 0:10 | 8:35 | 8:45
Setting up database |  | 0:30 | 0:45 | 8:45 | 9:30
Decorating model for backend |  | 0:30 | 2:00 | 10:00 | 12:00 | > fehler/bugs, ein kleiner fehler und suche in config aber falscher decorator
Creating repositories |  | 2:00 | 0:00 |  |  | mit querybuilder ärgern (normales sql tws soviel schöner)
Creating endpoints |  | 1:00 | 0:00
Implementing authentication |  | 2:00 | 0:00
Implementing transaction processing |  | 1:00 | 0:00
Start frontend project / setup |  | 0:10 | 0:00
Decorating model for frontend form generation |  | 1:00 | 0:00
Implemeting api connection |  | 2:00 | 0:00
Implementing state management |  | 1:30 | 0:00
Implemeting pages/components for services |  | 1:30 | 0:00
Acceptance testing |  | 1:00 | 0:00
0:00
Tasks between |  |  | 0:00
writing unit tests |  | 1:30 | 0:00
testing api with postman |  | 1:00 | 0:00
writing rest tests |  | 1:30 | 0:00
|  | 22:20 | 5:55